## Abstract of cost
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
ABSTRACT OF COST
Sr. | Description of work | quantities & amount
|  | Total Qty | Unit | unit Rate | Total amount
1 | Excavation for foundation, underground tanks (rectangular or square), trenches and drains in all kinds of soil including rock and removing all vegetation alongwith their roots and back filling selected excavated material in foundation, plinth or under floor | 2625.1687 | Cft
2 | Providing & laying 1:3:6 (1 cement 3 sand and 6 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete. | 6.8832 | Cft
3 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:4 in straight or curved walls 4-1/2" inches (114mm) and less in thickness including scaffolding, raking, out joints and curing, etc., complete in all floors. | 120.1745 | Cft
4 | Providing & laying 1:1.5:3 (1 cement 1.5 sand and 3 coarse aggregate) cement concrete using graded crush ¾ inch (20 mm) and down gauge in foundation including levelling, compacting and curing, etc., complete. | 6.875 | Cft
5 | 1/2" (13mm) thick cement plaster 1:4 on walls etc., including making edges, corners, and curing, etc., complete. | 142.0225 | Sft
6 | Providing and applying Vinyl emulsion (Distemper) Master/Dulux/Nippon/brighto/master paint, 2 coats including preparation of surface | 177.335 | Sft
7 | Providing and laying machine mixed reinforced cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge having a minimum works cube crushing strength of 3000 lbs.per sq. inch(20 N/mm2) at 28 days with a mix not leaner than 1:2:4 including form work and its removal, compacting and curing, etc., but excluding the cost of reinforcement in all floors including all lead and lift. | 11.2828 | Cft
8 | Providing & laying mild steel reinforcement bars with minimum yield stress of 40,000 Psi with and including the cost of straightening, cutting, bending, binding, wastage, and such overlaps as are not shown over the drawings, placing in position on cement concrete 1:2:4 precast or M.S. chairs, tying with binding wire, cost of chair and wires, etc., in all kinds of RCC work in foundation, basement, plinth, ground, and all floors of building including septic tank, underground tank and in projections for future extension. | 70.1082 | Kg
9 | Providing and placing of dry brick ballast in soakage pit & bed of pads (3/4''-1/2'' in size) | 19.9125 | Cft
10 | Earth filling under bed of water tank | -7.1042 | Cft
11 | Hand or machine boring for borehole tubewell in all types of soil rock, from a depth of up to 50 ft below ground level (only sweet potable water is acceptable after lab test in case of hard water contracor will make another borehole upto 3 holes), including sinking and withdrawing of casing pipe, complete. | 60 | Rft
12 | 2.5'' ɸ Providing and installing P.V.C. blind pipe, B.S.S. Class `B', (6 bar pressure/6kg/cm2) in tubewell bore hole, as casing including sockets and solvents and jointing with strainer, etc. complete (Pak Arab Jadeed/Hydroplast/National or equavalent reputeable company) | 50 | Rft
13 | Providing and installing, P.V.C. strainer B.S.S. Class 'B', in tubewell bore hole, as casing including sockets and solvents and jointing with blind casing pipe, etc.complete:- (Pak Arab Jadeed/Hydroplast/National or equavalent reputeable company) 2.5'' ɸ pipe | 10 | Rft
14 | Providing and fixing of DC Water pump (Shahzad/Javed), connecting with lead pipe, water tank complete in all respect including UPVC necessary specials (elbow, flunges, sockets, uniouns etc). | 1 | Job
15 | Providing and fixing 2 solar Panels -monocrystalline (175 watt each) Renogy, longi, JASCO or equavalent with aluminium Frame (warrented by the company) and fixing on frame/stands, provide and installing DC/AC copper cable 10 mm or recommended by the company length as per requirement (20-25 meter) connecting with DC water pump and the inverter/converter if required including a circuit breaking switch | 2 | Job
16 | Providing and installing 2 number of 100 amp/ah lead acid batteries (excide/AGS/OSAKA) connecting with DC water pump through a circuit breaker swithch, including auto charge controller upto 40 amp (Renogy Rover/Lumiax/SIMTEK or equavalent reputable company) or recommended for 100 amp batteries including on/off circuit breaking switch may be installed complete in all respect | 2 | No
17 | Supplying and installing 2 nubers of 850 litter water tank (flat 60''x48''x18'') Master including (i)- UPVC ball valve 3/4'' ɸ connecting with supply system (ii)- provide washout pipe with 1'' ɸ UPVC handle valve, UPVC 1'' ɸ pipe for over flow (10-15 feet), hot/cold jointing & connecting with water pad/khada, fixing of pipe with screw clamps complete in all respect. | 2 | Job
18 | Supplying and fixing 2 mumbers of 2.5'' (63 mm wide) MS strip 3 mm thick having a weight of 0.45kg/ft, around water tank for holding it, fixing with rawal bolts tighten in walls including welding/fixing hinges if required, two coats of oil painting on the strip (both sides), aprox length of one strip is 20' & weight is 9 Kg of one 20 feet strip | 1 | Job
19 | Supplying and installing of 1'' HDPE pipe (1.315 outer dia) in trenches and connecting with water pump and water tank in all respect with cutting, jointing, applying solution with all accessaries (bend, hot joints, sockets, bend, elbows, union etc) and installing non-return valves after every 500 feet or earlier | 1200 | Rft
20 | Supplying 3'' GI pipe (light) 8', welded with end plate, fixing in brick pillers with clamps & PCC 1:2:4, connecting with water tank through UPVC 1''(25 mm) ɸ pipe union joint and drilling & fixing 4 water tapes (3/4'' ɸ), welded GI sockets complete in all respect along with two coats of oil paint on pipe and sockets | 1 | Job
21 | Supplying and fixing 3/4'' ɸ bib cocks (master/3 star/Faisal or equavalent reputable company) complete in all respect | 4 | No
22 | Providing and fixing solar panels frame MS angle iron 35mmx35mmx3mm (weight 0.50 kg/foot length fixing the fram on constructed brick pillers complete in all respect (as per drawing given) | 1 | No
23 | Providing and fixing a steel plaque/plate 2'x1.5' 18 guage thick with embossed write up (provided by the organization) on water tank (raised plateform), included wooden beeding (oil painted) around the plate | 1 | Job
24 | Providing and fixing single leaf steel door (2'x2') 18 gauge sheet fixed with angle iron with locking arrangement and fixed round welded hinges | 4 | Sft
25 | Providing and fixing 3/4'' ɸ steel 3 mm thick (fine finished) grabs [1 foot long] fixed with rawal bolts in both sides of walls near water taps | 2 | No
26 | Providing and fixing 15-20 feet (as per site) long 3'' ɸ PVC drain pipe (as per site situation) good quality/Pak Arab/Jedda or equavelent, 3'' ɸ PVC bend/elbow, (steel Jali good quality 3'' ɸ) complete in all respect including excavation, fixing, connecting with drain waste complete in all respect. | 20 | Rft
27 | Collecting water samples in prescribed strelized water bottles providing to PCRWR/PHED labs, Paying cost for water quality tests (pre & post) according to PRCWR/PHED prescribed parameters and submitting to RDF | 2 | Job
| Sub Total |  |  |  | 0
All Taxes
| Grand Total Inclusive of all Taxes |  |  |  | 0

## Measur
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
MEAUREMENTS
Sr. No. | Descrioption | CFT Measurements |  |  |  |  | SFT Measurements
|  | Nos. | Length (FT) | Width (FT) D2 | Depth (FT) H | Volume (CFT) (DxExFxG) | Nos. | Length (FT) | Width (FT) | Area (SFT) (I*J*K=L)
1 | Excavation for foundation, underground tanks (rectangular or square), trenches and drains in all kinds of soil including rock and removing all vegetation alongwith their roots and back filling selected excavated material in foundation, plinth or under floor
1.1 | Trench for lead pipe | 1 | 1200 | 1 | 2 | 2400
1.2 | Raised platform for water Tank
| Long walls | 2 | 8.5 | 1 | 1 | 17
| Short walls | 2 | 2.5 | 1 | 1 | 5
1.3 | Water Pad
| Long walls | 2 | 8.25 | 1 | 0.25 | 4.125
| Short walls | 2 | 4.25 | 1 | 0.25 | 2.125
| Soakage pit (5' ɸ x 5') | 1 | 0.7855 | 25 | 5 | 98.1875
1.4 | Drain pipe
| Drain pipe | 1 | 20 | 1 | 1.5 | 30
| Total Qauntity:- |  |  |  |  | 2556.4375
2 | Providing & laying 1:3:6 (1 cement 3 sand and 6 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete.
Raised platform for water Tank
| Long walls | 2 | 8.25 | 1 | 0.25 | 4.125
| Short walls | 2 | 2.75 | 1 | 0.25 | 1.375
| Total Qauntity:- |  |  |  |  | 5.5
3 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:4 in straight or curved walls 4-1/2" inches (114mm) and less in thickness including scaffolding, raking, out joints and curing, etc., complete in all floors.
Raised platform for water Tank
| Long walls | 2 | 8 | 0.75 | 4.5 | 54
| Short walls | 2 | 2.75 | 0.75 | 4.5 | 18.5625
Water Pad
| Long walls | 1 | 8.25 | 0.75 | 1 | 6.1875
| Short walls | 2 | 4.25 | 0.75 | 1 | 6.375
| Brick pillars | 2 | 0.75 | 0.75 | 2 | 2.25
| Deduction of seat (edges of water pad) | 4 | 0.37 | 0.37 | 0.5 | -0.2738
| Deduction of steel door | 1 | 2 | 2 | 0.75 | -3
| Sub Total:- |  |  |  |  | 84.1012
| 10 % wastage of bricks |  |  |  |  | 8.4101
| Total Qauntity:- |  |  |  |  | 92.5113 | 1295.1585
4 | Providing & laying 1:1.5:3 (1 cement 1.5 sand and 3 coarse aggregate) cement concrete using graded crush ¾ inch (20 mm) and down gauge in foundation including levelling, compacting and curing, etc., complete.
Water Pad
| Bed of raised pad | 1 | 6.75 | 2.5 | 0.25 | 4.2188
| Bed of water pad/platform | 1 | 2.5 | 4.25 | 0.25 | 2.6562
| Total Qauntity:- |  |  |  |  | 6.875
5 | 1/2" (13mm) thick cement plaster 1:4 on walls etc., including making edges, corners, and curing, etc., complete.
Raised pad for water Tank
| Long walls | [5 empty] | 2 | 8.25 | 4.33 | 71.445
| Short walls | [5 empty] | 2 | 4 | 4.33 | 34.64
Water Pad/platform
| Long walls (sides) inner & outer | [5 empty] | 1 | 8.25 | 0.75 | 6.1875
| Long walls (Top) | [5 empty] | 1 | 8.25 | 0.75 | 6.1875
| Short walls (sides) inner & outer | [5 empty] | 2 | 5 | 0.75 | 7.5
| Short walls (Top) | [5 empty] | 2 | 5 | 0.75 | 7.5
| Brick pillars (9''x9''x2') [all 4 sides] | [5 empty] | 4 | 0.75 | 2 | 6
| Brick pillar (Top) | [5 empty] | 1 | 0.75 | 0.75 | 0.5625
| Edges of door | [5 empty] | 2 | 2 | 0.75 | 3
| Top & bottom | [5 empty] | 2 | 2 | 0.75 | 3
| Deduction of door (2'x2') | [5 empty] | 1 | 2 | 2 | -4
| Total Qauntity:- | [8 empty] | 142.0225
6 | Providing and applying Vinyl emulsion (Distemper) Master/Dulux/Nippon/brighto/master paint, 2 coats including preparation of surface
| Long walls of raised platform for water Tank | [5 empty] | 2 | 8.25 | 4.33 | 71.445
| Short walls of raised platform for water Tank | [5 empty] | 2 | 4 | 4.33 | 34.64
| Top | [5 empty] | 1 | 8.25 | 4 | 33
| L/W (inner side of wall) | [5 empty] | 2 | 6.75 | 2.5 | 33.75
| S/W (inner side of wall) | [5 empty] | 2 | 2.5 | 2.5 | 12.5
| Deduction of door (2'x2') two times (inner & outer) | [5 empty] | 2 | 2 | 2 | -8
| Total Qauntity:- | [7 empty] | Sft | 177.335
6 | Providing and laying machine mixed reinforced cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge having a minimum works cube crushing strength of 3000 lbs.per sq. inch(20 N/mm2) at 28 days with a mix not leaner than 1:2:4 including form work and its removal, compacting and curing, etc., but excluding the cost of reinforcement in all floors including all lead and lift.
| RCC slab for water platform (5'x4'x0.33') | 1 | 8.25 | 4 | 0.33 | 10.89
| Total Qauntity:- |  |  |  |  | 10.89
7 | Providing & laying mild steel reinforcement bars with minimum yield stress of 40,000 Psi with and including the cost of straightening, cutting, bending, binding, wastage, and such overlaps as are not shown over the drawings, placing in position on cement concrete 1:2:4 precast or M.S. chairs, tying with binding wire, cost of chair and wires, etc., in all kinds of RCC work in foundation, basement, plinth, ground, and all floors of building including septic tank, underground tank and in projections for future extension.
| Total Qauntity:- |  |  |  | KG | 49.201
Covering Slab of water platform
| Select 1/2'' Ø steel bars as main & distribution bars @ 6''C/C spacing and 1'' cover of from each side (5'x4' long slabs) | No of bars | Length (FT) | Hook (12d) | Over Lap (30d) | Total length of one bar | Total (Rft)
| Main bar | 16.34 | 8.095 | 0 | 0 | 8.095 | 132.2723 | KG | 40.0789 | KG
| Distribution bars (with hook) | 7.84 | 3.84 |  |  | 3.84 | 30.1056 | KG | 9.1221 | KG
| Total Qauntity:- | [7 empty] | 49.201 | KG
8 | Providing and placing of dry brick ballast in soakage pit & bed of pads (3/4''-1/2'' in size)
| Bed of raised pad | 1 | 6.75 | 2.5 | 0.33 | 5.5688
| Bed of water pad/platform | 1 | 6.75 | 4.25 | 0.5 | 14.3438
| Total Qauntity:- |  |  |  |  | 19.9125 | Cft
9 | Earth filling under bed of water tank | 1 | 6.5 | 2.5 | 0.91667 | 14.8958
| Deduction earth from bed excavation |  |  |  |  | -22
| Total Qauntity:- |  |  |  |  | -7.1042 | Cft
10 | Hand or machine boring for borehole tubewell in all types of soil rock, from a depth of up to 50 ft below ground level (only sweet potable water is acceptable after lab test in case of hard water contracor will make another borehole upto 3 holes), including sinking and withdrawing of casing pipe, complete.
| Boring | [7 empty] | 60 | Rft
| Total Qauntity:- | [7 empty] | 60 | Rft
11 | 2.5'' ɸ Providing and installing P.V.C. blind pipe, B.S.S. Class `B', (6 bar pressure/6kg/cm2) in tubewell bore hole, as casing including sockets and solvents and jointing with strainer, etc. complete (Pak Arab Jadeed/Hydroplast/National or equavalent reputeable company)
| 2.5" i/d | [7 empty] | 50 | Rft
| Total Quantity:- | [7 empty] | 50 | Rft
12 | Providing and installing, P.V.C. strainer B.S.S. Class 'B', in tubewell bore hole, as casing including sockets and solvents and jointing with blind casing pipe, etc.complete:- (Pak Arab Jadeed/Hydroplast/National or equavalent reputeable company) 2.5'' ɸ pipe | [7 empty] | Rft | 10
| Total Quantity:- | [7 empty] | Rft | 10
13 | Providing and fixing of DC Water pump (Shahzad/Javed), connecting with lead pipe, water tank complete in all respect including UPVC necessary specials (elbow, flunges, sockets, uniouns etc). | [7 empty] | Job | 1
| Total Quantity:- | [7 empty] | Job | 1
14 | Providing and fixing 2 solar Panels -monocrystalline (175 watt each) Renogy, longi, JASCO or equavalent with aluminium Frame (warrented by the company) and fixing on frame/stands, provide and installing DC/AC copper cable 10 mm or recommended by the company length as per requirement (20-25 meter) connecting with DC water pump and the inverter/converter if required including a circuit breaking switch | [7 empty] | Job | 2
| Total Quantity:- | [7 empty] | Job | 2
15 | Providing and installing 2 number of 100 amp/ah lead acid batteries (excide/AGS/OSAKA) connecting with DC water pump through a circuit breaker swithch, including auto charge controller upto 40 amp (Renogy Rover/Lumiax/SIMTEK or equavalent reputable company) or recommended for 100 amp batteries including on/off circuit breaking switch may be installed complete in all respect | [7 empty] | Job | 2
| Total Quantity:- | [7 empty] | Job | 2
16 | Supplying and installing 2 nubers of 850 litter water tank (flat 60''x48''x18'') Master including (i)- UPVC ball valve 3/4'' ɸ connecting with supply system (ii)- provide washout pipe with 1'' ɸ UPVC handle valve, UPVC 1'' ɸ pipe for over flow (10-15 feet), hot/cold jointing & connecting with water pad/khada, fixing of pipe with screw clamps complete in all respect. | [7 empty] | Job | 2
| Total Quantity:- | [7 empty] | Job | 2
17 | Supplying and fixing 2 mumbers of 2.5'' (63 mm wide) MS strip 3 mm thick having a weight of 0.45kg/ft, around water tank for holding it, fixing with rawal bolts tighten in walls including welding/fixing hinges if required, two coats of oil painting on the strip (both sides), aprox length of one strip is 20' & weight is 9 Kg of one 20 feet strip | [7 empty] | Job | 1
| Total Quantity:- | [7 empty] | Job | 1
18 | Supplying and installing of 1'' HDPE pipe (1.315 outer dia) in trenches and connecting with water pump and water tank in all respect with cutting, jointing, applying solution with all accessaries (bend, hot joints, sockets, bend, elbows, union etc) and installing non-return valves after every 500 feet or earlier | [7 empty] | Rft | 1200
| Total Quantity:- | [7 empty] | Rft | 1200
19 | Supplying 3'' GI pipe (light) 8', welded with end plate, fixing in brick pillers with clamps & PCC 1:2:4, connecting with water tank through UPVC 1''(25 mm) ɸ pipe union joint and drilling & fixing 4 water tapes (3/4'' ɸ), welded GI sockets complete in all respect along with two coats of oil paint on pipe and sockets | [7 empty] | Job | 1
| Total Quantity:- | [7 empty] | Job | 1
20 | Supplying and fixing 3/4'' ɸ bib cocks (master/3 star/Faisal or equavalent reputable company) complete in all respect | [7 empty] | No | 4
| Total Quantity:- | [7 empty] | No | 4
21 | Providing and fixing solar panels frame MS angle iron 35mmx35mmx3mm (weight 0.50 kg/foot length fixing the fram on constructed brick pillers complete in all respect (as per drawing given) | [7 empty] | Job | 1
| Total Quantity:- | [7 empty] | Job | 1
22 | Providing and fixing a steel plaque/plate 2'x1.5' 18 guage thick with embossed write up (provided by the organization) on water tank (raised plateform), included wooden beeding (oil painted) around the plate | [7 empty] | Job | 1
| Total Quantity:- | [7 empty] | Job | 1
23 | Providing and fixing single leaf steel door (2'x2') 18 gauge sheet fixed with angle iron with locking arrangement and fixed round welded hinges | [5 empty] | 1 | 2 | 2 | 4
| Total Quantity:- | [7 empty] | Sft | 4
24 | Providing and fixing 3/4'' ɸ steel 3 mm thick (fine finished) grabs [1 foot long] fixed with rawal bolts in both sides of walls near water taps | [8 empty] | 2
| Total Quantity:- | [7 empty] | No | 2
25 | Providing and fixing 15-20 feet (as per site) long 3'' ɸ PVC drain pipe (as per site situation) good quality/Pak Arab/Jedda or equavelent, 3'' ɸ PVC bend/elbow, (steel Jali good quality 3'' ɸ) complete in all respect including excavation, fixing, connecting with drain waste complete in all respect. | [7 empty] | Rft | 20
| Total Quantity:- | [7 empty] | Rft | 20
26 | Collecting water samples in prescribed strelized water bottles providing to PCRWR/PHED labs, Paying cost for water quality tests (pre & post) according to PRCWR/PHED prescribed parameters and submitting to RDF | [7 empty] | Job | 2
| Total Quantity:- | [7 empty] | Job | 2
#REF!
#REF!
#REF!

## S. pit
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
Plan of soakage Pit (5' Ø x5' deep)
1/2'' Ø bars @ 9'' c/c spacing
[8 empty] | 4'-9'' | 2 bars
[8 empty] | 3'-6'' | 4 bars
[8 empty] | 2'-0'' | 4 bars
[8 empty] | 0'-9'' | 4 bars
X-Sec of Pit (5' Ø x5' deep)
| 3'' | [6 empty] | RCC 1:2:4 for Pit slab
| 5' | [7 empty] | 1.5
GL
Ordinary masonery in 1:4 CM
1.5
|  |  | 4.5'' |  |  | 4.5''
4.25'
3'
Honey combing Masonary in 1:4 CM
| 3'' | [5 empty] | 3'' | 3'' thick brick/stone ballast
|  | 6'' |  |  | 6''
4.25'
0.37'
4.25'
0.37'

## M-Soak pit
Strengthening Participatory Organization (SPO)
Detailed Estimate for Soakage Pit (5' ф x 5')
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
DETAIL MEASUREMENTS
Sr. No. | Descrioption |  | CFT Measurements |  |  |  |  | SFT Measurements
|  |  | Nos. | Length (FT) | Width (FT) D2 | Depth (FT) H | Volume (CFT) (DxExFxG) | Nos. | Length (FT) | Width (FT) | Area (SFT) (I*J*K=L)
1 | Excavation for foundation, underground tanks (rectangular or square), trenches and drains in all kinds of soil including rock and removing all vegetation alongwith their roots and back filling selected excavated material in foundation, plinth or under floor
| Excavation for pits (∏D2/4xdepth |  | 1 | 0.7855 | 25 | 3.5 | 68.7313
| Total Qauntity:- | [5 empty] | 68.7313
2 | Providing & laying 1:3:6 (1 cement 3 sand and 6 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete.
| Excavation for pits (∏D2/4xdepth |  | 1 | 5.5326 |  | 0.25 | 1.3832
| Total Qauntity:- | [5 empty] | 1.3832
3 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:4 in straight or curved walls 4-1/2" inches (114mm) and less in thickness including scaffolding, raking, out joints and curing, etc., complete in all floors.
| pits (∏D2/4)-(∏D2/4)xdepth |  | 1 | 5.5326 |  | 5 | 27.6632
| Total Qauntity:- | [5 empty] | 27.6632 |  |  | Nos | 387.2848
4 | Providing and laying machine mixed reinforced cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge having a minimum works cube crushing strength of 3000 lbs.per sq. inch(20 N/mm2) at 28 days with a mix not leaner than 1:2:4 including form work and its removal, compacting and curing, etc., but excluding the cost of reinforcement in all floors including all lead and lift.
| Top cover/slab of pits (∏D2/4)xdepth |  | 2 | 0.7855 | 25 | 0.25 | 0.39275
| Total Qauntity:- |  |  |  | Cft |  | 0.39275
5 | Providing & laying mild steel reinforcement bars with minimum yield stress of 40,000 Psi with and including the cost of straightening, cutting, bending, binding, wastage, and such overlaps as are not shown over the drawings, placing in position on cement concrete 1:2:4 precast or M.S. chairs, tying with binding wire, cost of chair and wires, etc., in all kinds of RCC work in foundation, basement, plinth, ground, and all floors of building including septic tank, underground tank and in projections for future extension.
| Select 1/2'' Ø bars as main and distribution for Covering slab for pits @ 6'' C/C spacing |  | No | No of bars | Length | Total length (Rft) | weight of bars (Lbs) | weight of bars (Kg)
|  | Centeral bars | 2 | 2 | 4.75 | 19 | 12.692 | 5.7571
|  |  | 2 | 4 | 3.5 | 28 | 18.704 | 8.4841
|  |  | 2 | 4 | 2 | 16 | 10.688 | 4.848
|  |  | 2 | 4 | 0.75 | 6 | 4.008 | 1.818
|  | Total |  |  |  | 69 | 46.092 | 20.9072
Total Qauntity:- (in Rft)

## steel SP
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
Steel Febrication for Slab of Soakage pit Pit
use 1/2'' Ø bars as Main and distribution bars @ 9'' c/c spacing
4'-3''
Chod Formula
|  |  | 4'-9'' | 2 bars
|  |  | 3'-6'' | 4 bars
|  |  | 2'-0'' | 4 bars
|  |  | 0'-9'' | 4 bars
5'
5'

## Solar frame
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
Frame for solar pannels
Size of solar pannel 175 watt longi |  |  |  | MS angle iron 25mmx25mmx3mm (weight 1.12kg/m or 0.341 kg/foot length
length 52.2 x wide 26.3 x thick 1.38 in
[7 empty] | Length | No | Total
|  | 52.6' |  |  |  | Sides | 52.2 | 2 | 104.4
[6 empty] | Top&Bottom | 52.6 | 3 | 157.8
| 52.2' |  |  |  |  | legs rear | 4 | 2 | 8
[6 empty] | legs front | 0.75 | 2 | 1.5
[8 empty] | Rft | 271.7
[8 empty] | KG | 92.6497
[8 empty] | Mond | 2.3162
1.5'
| Brick Masonry in 1:4 |  | 9''x9'' Brick Masonry in 1:4
[5 empty] | 1.5' | Ground level
PCC 1:2:4
#REF!
#REF!

## water Pad
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
Plan & X-Sec of platform 5'x 8.25' x4.33
|  |  |  | 5' |  |  | 4'
|  |  | 8.25' |  | 9'' |  |  |  |  | 8.25'
| 2 no of 9''x9''x2' brick pillars |  |  |  | 4.25 |  |  | 2.5
|  |  |  | 9'' |  | A |  |  | A'
Plateform for water Tank (8.25'x4x4.33')
| Soakage pit (5' ɸx5' |  |  |  | 3/4'' steel coated bib cocks (long)
9''
X-Sec of Platform
wall of tank
|  |  |  | 9'' | 4.25'
|  | 1' | 6''
|  |  | 3'' |  | 3'' thick PCC 1:1.5:3
|  |  | 3'' |  | 6'' thick Dry rammed Brick ballast
3''
5.75' & 5.37'
#REF!
#REF!
3'' drain PVC pipe
3'' ɸ GI pipe

## Platform
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
Plan & X-Sec of platform 5' x 4'x 4.33'
8.25'
2.5'' wide & 3 mm thick M/S strip (0.45kg/ft) fixed with rawal bolts to hold the water tank aprox length is 20' each & weigt of 20' strip is 9 KG
|  | 3/4'' ɸ steel grabs (1' long) 2 nos | [8 empty] | 4'' | 4''
|  |  |  | 1'' (25 mm) ɸ PPR-pipe | [6 empty] | 2.5' | 4'-6''
1'' (25 mm) ɸ gate/ball valve
[6 empty] | 9'' |  |  | 9''
4.5''
[7 empty] | PCC 1:1.5:3 |  |  |  | 3''
1.5' | [6 empty] | Dry rammed Brick ballast |  |  |  | 4''
| Soak pit 5' ɸ x5' | [5 empty] | earth filling |  |  |  | 11''
3.5' | [10 empty] | 9''
6.75
[11 empty] | 3'' | 3''
| 4.75' |  |  |  | PCC 1:3:6 |  |  | PCC 1:3:6
[5 empty] | 1' |  |  | 1'
#REF!
#REF!
single leaf steel door (2'x2') 18 gauge M/S Sheet with angle iron frame & locking arrangements
3'' dia G.I pipe
20' long 3'' ɸ drain PVC pipe

## Loc-Plan
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
Location Plan
N
Village Yar Muhammad Khoso
|  |  | Link path way to village (about 1 KM) |  | SPO Office District Sohbatpur
Main Sohbat Put-Sui Road
Approx: 6 KM from SPO office

## Site Plan
Strengthening Participatory Organization (SPO)
Emergency Response office-District Sohbat Pur -Balochistan, Pakistan
Installation of drinking water supply schemes under Milenda Gates Foundation Funded Project at Yar Muhammad Khoseo UC Gandar District Sohbat Pur (Doubble Tank with Pit 5' ɸ x 5' deep)
Site Plan at village Yar Muhammad Khose District Sohbat Pur (Balochistan)
Pond
PHED Over head Tank
Proposed platform/Tank
|  | 1100 Rft |  |  | Link path way to village (about 1 KM)
4 Installed Hand pumps
One is functional
Proposed Borehole
Main Sohbat Pur-Sui Road
Lands
Lands